## Sheet1
Task | Start Date | Estimates | Status
Project Kick off | 2020-05-27 | 7 | Complete
Understanding the effort | 2020-06-03 | 10 | Complete
Creation of Base Project plan | 2020-06-10 | 12 | Complete
Meetings with stakeholders | 2020-06-25 | 10 | Complete
Phase 1 | 2020-07-05 | 8 | In Progress
Phase 2 | 2020-07-11 | 8 | In Progress
Phase 3 | 2020-07-21 | 9 | In Progress
Phase 4 | 2020-07-30 | 7 | In Progress
Review of the Project | 2020-08-06 | 5 | Not Started
Quality Testing | 2020-08-11 | 12 | Not Started
Project Deployment | 2020-08-23 | 3 | Not Started